## Sheet1
Deadlines/Deliverables - Dates and Work Division |  | Team Members
|  | Anne Lin | Chandan Suri | Xingcheng Rong | Yunchen Yao | Ziwei Han
2022-02-21 | Background
Data Desccription
Proposed ML Techniques
2022-03-21 | Data Exploration/Analysis
Cleaning and Sampling - Data Preprocessing
Drawing insights from Data Exploration - Visualizations
Exploring Different ML Approaches
Presentation Preparation
Presentation Delivery
2022-04-25 | Finalizing Data Pre-Processing
Preparation of Cool Visualizations
ML Implementation - Exploring Different Approaches
Finalizing ML Approach
Finalizing and Preparing the code
Report Preparation
Finalizing the Report and Code DB